## Sheet 1
Risk Assessment
Risk | Likelihood | Mitigated | Plan in Progress | Who
Regional Power Outage | Low | No | No
Local Power Outage | Moderate | No | No
Weather Event | Moderate | N/A | Monitor Starting 1/3 | Rick
Wifi Unavailable/No vote.WA.gov | Moderate/High | No | Plan started | EIT Leadership
Cell Phone Coverage in Bldg. Unavalable/Poor | Moderate/High | No | No
Potential Demonstrations | Low
Power cords unavailable for Precinct Tables | High | No | ?
Power cords unavailable for Credentialling | High | No | ?
Some PCs will not be adequate for Credentialling | Moderate | No | EIT Group working on requirements
Printers may be required for some tasks?? | Moderate |  | ??
Inadequate Parking parking on site | Low |  | ??
Covid | Moderate | N/A